Chữa đề buổi 1

PMG201c - Final Practice Examination #1

Look at projects that you are involved with, have been involved with OR the projects going on around you. Select one project in your studying fields at FU (i.e software project for SE), give the solutions or answers for following requests based on your understanding about the project & assumptions

Request 1:

give detailed descriptions for the project in which you mention clearly its key characteristics: project title, project purpose/objectives (unique), project timeframe (temporary), customer/sponsor (clearly defined), project milestones (time constraints) and other project constraints (cost, resources).

Project Title: FPT Student Learning Management (SLM) System

Project Purpose/Objectives:

The purpose of the SLM system is to facilitate efficient management and tracking of learning progress for both professors and students in FPT university . Key objectives include:

1. Providing administrators with tools to configure the system, manage subject information, and oversee user management.

2. Empowering professors to access assigned classes, monitor student lists, and evaluate student performance for each class.

3. Enabling students to register, access allocated classes, participate in online testing, submit assignments, and review evaluations from professors .

4. Generating reports on student grades, either by class or subject, to support academic assessment and decision-making processes.

Project Timeframe:

The project is scheduled to be completed within 4 months, encompassing all phases of the software development life cycle, from requirements gathering to deployment.

Customer/Sponsor:

The primary customer and sponsor of the project is FPT University

The to-be potential customer of the project is the academic institution or educational organization that will utilize the Student Learning Management System. This could be a university, college, or any institution offering academic courses.

Project Milestones: Waterfall model

1. Requirements Gathering and Analysis (Week 1-2)

2. System Design  (Week 3-4)

3. Development and UT Testing (Week 5-10)

4. Testing (IT, ST, UAT)  (Week 11-12)

5. Deployment   (Week 13-16)

Project life cycle -

Plan-driven Waterfall

Change-driven Agile , Iterative incremental

Project management process

1- Initiating

2- Planning

3 - Executing

4- Monitoring and Controlling

5- Closing

Other Project Constraints:

- Cost: The project budget is 10000 $

- Resources: The project team consists of 3 developers, 1 testers, 2 designers, 2 BA and project managers who must collaborate efficiently to meet project deadlines.

- Technology Stack: Backend: spring boot. Front end : Angular .

Deployment Environment : AWS Cloud

Request 2 : what type of organization you think the project using and what type of organization you think that should or should have used along with the reasons for this? Provide relevant reasons for your answers

Considering the criticality of timely delivery and the need for close coordination among team members, a projectized organization structure could be more suitable. In a projectized structure, resources are dedicated exclusively to the project, leading to a more focused approach and faster decision-making. This would be beneficial for meeting the tight 4-month timeframe of the project.

Reasons for Choosing a Projectized Organization:

1. Clear Project Focus: In a projectized structure, team members are solely dedicated to the project, ensuring undivided attention and focus on meeting project objectives within the specified timeframe.

2. Streamlined Communication: With a dedicated project team, communication flows more smoothly, leading to quicker decision-making and problem-solving.

4. Accountability: Each team member has clear roles and responsibilities within the project, enhancing accountability and ownership of tasks.

By adopting a projectized organization structure, the project team can maximize efficiency, minimize delays, and ensure successful delivery of the Student Learning Management System within the stipulated 4-month timeframe.

Request 3 Create the project WBS in bullet format with following 4 levels

• Level 1 & 2 are the project stages/phases and their relevant iterations/sprints.

• Level 3 includes the project documents (project management, engineering) and project release/deliverable names (if any) in each iteration/sprint.

• Level 4 includes the work packages (screens, functions) for each release/deliverable

WBS THEO WATERFALL:

Student Learning Management System

Phase 1: Initiating (level 1)

1.1.2 Create Project Charter (level 2 )

1.1.2.1 Solidifying the project scope (level 3)

1.1.2.2 Determine resources needed (level 3)

1.1.2.3 Define project SMART goal and deliverables (level 3)

1.1.3 Get project charter approval (level 2)

1.1.4 Hold a kick-off meeting (level 2)

1.1.5 Perform a cost-benefit analysis for the project (level 2)

1.1.6 Create stakeholder Register (level 2)

1.2 Phase 2: Planning (level 1)

1.2.1 Create Project management plan (level 2)

1.2.1.1 Scope Management Plan (level 3)

1.2.1.2 Time/Schedule  Management Plan (level 3)

1.2.1.3 Cost Management Plan (level 3)

1.2.1.4 Risk Management Plan (level 3)

1.2.1.5 Resource Management Plan (level 3)

1.2.1.6 Communication Management Plan (level 3)

1.2.1.7 Stakeholder management Plan (level 3)

1.2.1.8 Procurement Management Plan (level 3)

1.2.1.9 Quality Management Plan (level 3)

1.2.1.10 Integration Management Plan

1.2.2 Meeting with team to discuss plans (level 2)

1.2.3 Deliver Project Management Plan (level 2)

1.3 Phase 3 Executing (level 1) (Analysis, Design, Code, Test)

1.3.1 Requirement Analyse  (level 2)

1.3.1.2 BRS – Business requirement specification (level 3)

1.3.1.3 SRS –System requirement specification (level 3)

1.3.1.4 Perform Requirement validation (level 5)

1.3.1.5 Perform Requirement management (level 5)

1.3.2 Design (level 2)

1.3.2.1 Basic design for SLM   (level 3)

1.3.2.2Detail design for SLM  (level 3)

1.3.3 Implementing (level 2)

1.3.3.1 Code package for module 1,2,3,4 (level 3):

1.3.3.1.1 Authentication feature (level 4)

1.3.3.1.2 Student management feature (level 4)

1.3.3.1.3 Professor management feature (level4)

1.3.3.1.4 Admin feature (level 4)

1.3.3.2 Unit test case  (level 3)

1.3.3.3 Unit test report (level 3)

1.3.3.4 Testing (level 3)

1.3.3.4.1 Test Plan (IT,ST,UAT) module 1,2,3,4

1.3.3.4.2 Test case (IT,ST,UAT) module 1.2,3,4  (level 4)

1.3.3.4.3 Test report (IT,ST,UAT) for module 1,2,3,4    (level 4)

1.3.4 Deployment  (level 2)

1.3.4.1 Buy server, test device (level 3)

1.3.4.2 Setting server (level 3)

1.3.4.3 Deploy code release 1 in staging environment(level 3)

1.3.4.4 Testing in staging environment (level 3)

1.3.4.4 Deploy code in product environment(level 3)

1.3.4.5 Testing in product environment (level 3)

1.4 Phase 4: Monitoring and Controlling (level 1)

1.4.1 Control scope (level 2)

1.4.2 Track progress (level 2)

1.4.3 Perform Cost control (level 2)

1.4.4 Monitor and control Risk (level 2)

1.5 Phase 5: Closing (level 1)

1.5.1 Lesson learn (level 2)

1.5.2 Project Final Report (level 2)

1.5.3  Project Archive (level 2)

WBS theo Iterative Incremental : 
Student Learning Management System

Phase 1: Initiating (level 1)

1.1.1 Create Project Proposal  1.1.2 SF

1.1.2 Create Project Charter  1.1.3 SF

1.1.2.1 Solidifying the project scope (level 3)

1.1.2.2 Determine resources needed (level 3)

1.1.2.3 Define project SMART goal and deliverables (level 3)

1.1.3 Get project charter approval   1.1.2 FS

1.1.4 Hold a kick-off meeting (level 2)

1.1.5 Perform a cost-benefit analysis for the project (level 2)

1.1.6 Create stakeholder Register (level 2)

1.2 Phase 2: Planning (level 1)

1.2.1 Create Project management plan (level 2)

1.2.1.1 Scope Management Plan (level 3)

1.2.1.2 Time Management Plan (level 3)

1.2.1.3 Cost Management Plan (level 3)

1.2.1.4 Risk Management Plan (level 3)

1.2.1.5 Resource Management Plan (level 3)

1.2.1.6 Communication Management Plan (level 3)

1.2.1.7 Stakeholder management Plan (level 3)

1.2.1.8 Procurement Management Plan (level 3)

1.2.1.9 Quality Management Plan (level 3)

1.2.2 Meeting with team to discuss plans (level 2)

1.2.3 Deliver Project Management Plan (level 2)

1.3 Phase 3 Executing (level 1) (Analysis, Design, Code, Test)

1.3.1 Requirement Analyse  (level 2)

1.3.1.2 BRS – Business requirement specification (level 3)

1.3.1.3 SRS – System requirement specification (level 3)

1.3.1.4 Perform Requirement validation (level 5)

1.3.1.5 Perform Requirement management (level 5)

1.3.2 Iteration 1 – (Level 2)

1.3.2.1 Design (level 3)

1.3.2.1.1 Basic design for module 1 Authentication feature   (level 4)

1.3.2.1.2 Detail design for module 1 Authentication  feature (level 4)

1.3.2.2 Implementing (level 3)

1.3.2.2.1 Code package for module 1: Authentication feature (level 4) (use-case 1 to 10)

1.3.2.2.2 Unit test case (level 4)

1.3.2.2.3 Unit test report (level 4)

1.3.2.3 Testing (level 3)

1.3.2.3.1 Test Plan (IT,ST,UAT) module 1

1.3.2.3.2 Test case (IT,ST,UAT) module 1  (level 4)

1.3.2.3.2 Test report (IT,ST,UAT) for module 1   (level 4)

1.3.3 Iteration 2 – (level 2)

1.3.3.1 Design (level 3)

1.3.3.1.1 Basic design  for module 2, 3 (level 4)

1.3.3.1.2 Detail design for module 2 , 3  (level 4)

1.3.3.2 Implementing (level 3)

1.3.3.2.1 module 1`s updated Codepackage  (level 4)

1.3.3.2.2 Code package for module 2: Student management feature (level 4)

1.3.3.2.3 Code package for module 3: Professor management feature (level4)

1.3.3.2.4 Unit test case for module 2,3(level 4)

1.3.3.2.5 Unit test report for module 2,3(level 4)

1.3.3.3 Testing (level 3)

1.3.3.3.1 Test Plan (IT,ST,UAT) module 2.,3

1.3.3.3.2 Test case (IT,ST,UAT) module 2,3  (level 4)

1.3.3.3.2 Test report (IT,ST,UAT) for module 2,3    (level 4)

1.3.4 Iteration 3 – level 2

1.3.4.1 Design (level 3)

1.3.4.1.1 Basic design for module 4  (level 4)

1.3.4.1.2 Detail design for module 4  (level 4)

1.3.4.2 Implementing (level 3)

1.3.4.2.1 module 1`s updated Codepackage (level 4)

1.3.4.2.2 code package for module 4: Admin feature (level 4)

1.3.4.2.3 Unit test case for module 4(level 4)

1.3.4.2.4 Unit test report for module 4(level 4)

1.3.4.3 Testing (level 4)

1.3.4.3.1 Test Plan (IT,ST,UAT) module 4

1.3.4.3.2 Test case (IT,ST,UAT) module 4  (level 4)

1.3.4.3.3 Test report (IT,ST,UAT) for module 4    (level 4)

1.3.5 Deployment  (level 2)

1.3.4.1 Buy server, test device (level 3)

1.3.4.2 Setting server (level 3)

1.3.4.3 Deploy code release 1 in staging environment(level 3)

1.3.4.4 Testing in staging environment (level 3)

1.3.4.4 Deploy code in product environment(level 3)

1.3.4.5 Testing in product environment (level 3)

1.4 Phase 4: Monitoring and Controlling (level 1)

1.4.1 Control scope (level 2)

1.4.2 Track progress (level 2)

1.4.3 Perform Cost control (level 2)

1.4.4 Monitor and control Risk (level 2)

1.5 Phase 5: Closing (level 1)

1.5.1 Lesson learn (level 2)

1.5.2 Project Final Report (level 2)

1.5.3  Project Archive (level 2)

WBS theo Agile Scrum

Student Learning Management System - Level 1

1. Project Initiation – level 2

1.1 Define project scope and objectives – level 3

1.2 Identify stakeholders and their requirements– level 3

1.3 Create project charter– level 3

1.3- Define project scope and objectives – level 4

1.4 Define project team roles and responsibilities– level 3

1.5  Conduct project kickoff meeting– level 3

2. Sprint 0: Planning and Setup– level 2

2.2 Create product backlog and prioritize features– level 3

2.3 Define sprint cycles and timelines– level 3

2.4 Set up development environment and tools– level 3

2.5 Define Definition of Done (DoD) – level 3

2.6 Develop release plan– level 3

3. Sprint 1– level 2

3.1 Sprint planning meeting– level 3

3.2 Develop user stories for sprint – level 3

3.3 Define sprint backlog and tasks– level 3

3.4 Develop software architecture and design– level 3

3.5 Implement core functionalities of Student Learning Management – level 3

3.6 Conduct daily scrum meetings– level 3

3.7 Test and validate sprint deliverables– level 3

3.8 Conduct sprint review and retrospective– level 3

4. Sprint 2– level 2

4.1 Sprint planning meeting– level 3

4.2 Develop user stories for sprint– level 3

4.3 Define sprint backlog and tasks– level 3

4.4 Implement additional functionalities of Student Learning Mangement System– level 3

4.5 Conduct daily scrum meetings– level 3

4.6 Test and validate sprint deliverables– level 3

4.7 Conduct sprint review and retrospective– level 3

5. Sprint 3– level 2

5.1 Sprint planning meeting– level 3

5.2 Develop user stories for sprint– level 3

5.3 Define sprint backlog and tasks– level 3

5.4 Implement remaining functionalities of Student Learning Management System– level 3

5.5 Conduct daily scrum meetings– level 3

5.6 Test and validate sprint deliverables– level 3

5.7 Conduct sprint review and retrospective– level 3

6. Sprint 4: Release and Deployment– level 2

6.1 Conduct final sprint planning meeting– level 3

6.2 Test and validate final release– level 3

6.3 Conduct final sprint review and retrospective– level 3

6.4 Deploy Student Learning Management System to production environment– level 3

6.5 Conduct post-release testing and monitoring– level 3

6.6 Close out project– level 3

Request 4

a. Define at least 5 roles you might have in your project team and at least 2 responsibilities (mapped to the project work packages and/or activities) for each role.

b. Create a Responsibility Assignment Matrix (RAM) in which you need to create 10 work packages or activities which can be assigned to the team and you need to come up with specific team members or roles who will complete this work (R-Responsible, A-Accountable, C-Consult, or I-Inform)

Answer

a ) 
Case 1 Waterfall : (V model, Iterative incremental đều dùng)

Project manager: Internal stakeholder, planning and organizing, managing tasks, budgeting, controlling costs and other factors. Everything they do helps make sure the project can be completed on time and on budget, and more importantly profitable.

BA: Internal stakeholder bridges the gap between external stakeholders and the development team, interpreting business requirements into understandable development tasks to match a final software product with the expected business value

Developer team : internal stakeholder , He writes, debugs and executes the source code of a software application.

Designer team : internal stakeholder A UI/UX designer’s job is to create user-friendly interfaces that enable users to understand how to use complex technical products

Tester team : Internal stakeholder. The role of a tester is to test out products for bug and provide reports to the project teams about any issues or improvements that the product may require

Customer;.. external stakeholder plays a vital role in providing requirements, feedback, and validation during the product development or service delivery process. Their satisfaction and adoption of the product/service are crucial for business success and growth.

Vendor X : external stakeholder. Those vendor whom collaborate with our team to ensure timely and accurate delivery of services

Case 2: Agile Scrum

Scrum master : A Scrum Master chiefly acts as  a coach and facilitator to the Scrum Team . He helps the team to assign user stories with top priority into sprints

BA: bridges the gap between external stakeholders and the development team, interpreting business requirements into understandable development tasks to match a final software product with the expected business value

Developer team : internal stakeholder , He writes, debugs and executes the source code of a software application.

Tester team : Internal stakeholder. The role of a tester is to test out products for bug and provide reports to the project teams about any issues or improvements that the product may require

Product owner  – external stakeholder from customer , give teams the requirement , user story . They review the output after each sprints

b)

Raci -  Responsibility assignment matrix – R -A -C -I

R Responsible : sẽ là người chịu trách nhiệm làm  chính cho công việc đó , có thể bao gồm nhiều 1 R

A Accountable  : sẽ là người chịu trách nhiệm cho công việc của R , thường chỉ có 1 A cho công việc đó

C consult : tham vấn C, xin ý kiến

I inform : người i, ko tham trực tiếp vào công việc nhưng khi cần , họ phải được biết về kết quả của công việc đó

Case 1 : RACI waterfall / iterative / V model

|  | PM- | BA – | Developer | Tester | Customer |
| --- | --- | --- | --- | --- | --- |
| Create project charter | R/A | C | C | C | I |
| Create SRS | A | R | C | I | C/R |
| Create BD | A | R | C | I/C | C |
| Create DD | A | C | R(senior) | I/C | I |
| Implement coding | A | C | R | C | I |
| Create test scenario/test case | A | R | C | R | C |
| Perform testing | A | I | C | R | I |

Vd trình bày RACI khi thi EOS  mà ko kẻ bảng đc

RACI chart :

Create project charter PM(R) , BA(C) , Dev(C), Tester (C), Customer (C)

Create SRS: PM(A), BA(R), Dev(C), Tester (C), Customer (C/R)

Create BD:  PM(A) , BA(R) , Dev(C), Tester (I/C), Customer (C)

Create DD:  PM(A) , BA(C) , Dev(R), Tester (I/C), Customer (I)

Implement coding :  PM(A) , BA(C) , Dev(R), Tester (C), Customer (I)

Create test scenario/ test case: PM(A) , BA(R) , Dev(C), Tester (R), Customer(C)

Perform testing: PM(A) , BA(I) , Dev(C), Tester (R), Customer(I)

Case 2 : RACI AGILE SCRUM 
Raci chart

|  | Scrum Master | BA – | Developer | Tester | PO -product owner |
| --- | --- | --- | --- | --- | --- |
| Create product backlog | R | C | C | I | R/A |
| Create Sprint backlog | R | C | C | C | A |
| Create Basic Design | C | R | C | I | A |
| Implement coding | C | C | R | C | A |
| Perform testing | C | I | C | R | A |

Request 5 : Identify at least 3 significant risks that you think the project faces. For each risk determine how likely you think it is to occur (the probability) and the impact if it does occur. Create your own scoring system for probability and impact. You might use High-Medium-Low; you might use numeric values or you might use percentages. Define a response for each of these risks.

Risk title 1 : Wrong budget estimate and cost overruns

Possibility : Low

Impact: High

Mitigation Plan: add little amount of buffer for the budget (around 10%) , careful estimation. Strictly control the scope to avoid scope creep , Get Change request (CRs) signed when there are out of scope demands from customer. Monitor cost and progress weekly to detect early signs of overrun

Contingency Plan: Cut down on the project scope ( nice to have features) . Negotiate with the customer to move some part to the next phase. Temporarily assign higher-performing team members to speed up delivery.

Risk title 2 : The project schedule is too tight; it’s hard to complete this project on time

Possibility : Low

Impact: High

Mitigation Plan: Set The priority for each of the activity, add buffer for task

Contingency Plan: Negotiate with customer to reschedule . Add more member into key task in order to fast up the delivery . Force team to OT. Do keys task in parallel if possible

Risk title 3 : Project manager has poor management skill

Possibility : Medium

Impact: Medium

Mitigation Plan: Plan  leadership training for manager, provide PM learning material on Udemy

Contingency Plan: choose another one as a sub PM in order to support management task

Risk title 4 : A lack of cooperation negatively affects your member productivity

Possibility : Medium

Impact: Medium

Mitigation Plan: Encourage each team member in his task, and inspire them to greater efforts

Contingency Plan: Encourage each team member in his task, and inspire them to greater efforts