## WBS
Work Breakdown Structure | [5 empty] | Library Management
| Project Start | 2023-11-25
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Phase 1: Initial project
2 | 1.1 | Creat project charter
2 | 1.2 | Creat project plan
1 | 2 | Phase 2: Analyst requiremt
2 | 2.1 | Elicitation
3 | 2.1.1 | Libararian survey
3 | 2.1.2 | Student survey
2 | 2.2 | Document
3 | 2.2.1 | Draw wireframe
3 | 2.2.2 | Write SRS
2 | 2.3 | Review + update SRS | `
1 | 3 | Phase 3: Design
2 | 3.1 | Design UI
2 | 3.2 | Design DB
| 3.3 | Design architecture system
2 | 3.4 | Review DB, Architecture system
1 | 4 | Phase 4: Implementation
2 | 4.1 | Inter 1 - Release 1
3 | 4.1.1 | Account Management
4 | 4.1.1.1 | Login
4 | 4.1.1.2 | Logout
4 | 4.1.1.3 | Register account
4 | 4.1.1.4 | View profile
4 | 4.1.1.5 | Update profile
4 | 4.1.1.6 | View account list
4 | 4.1.1.7 | View accout detail
3 | 4.1.2 | Book Management
4 | 4.1.2.1 | View book list
4 | 4.1.2.2 | View book detail
4 | 4.1.2.3 | Search book
4 | 4.1.1.4 | Add book
4 | 4.1.1.5 | Update book
4 | 4.1.1.6 | Delete book
| 4.1.3 | Fix bug release 1
2 | 4.2 | Inter 2 - Release 2
3 | 4.2.1 | Borrow book
4 | 4.2.1.1 | Add book to cart
4 | 4.2.1.2 | View cart
4 | 4.2.1.3 | Creat ticket borrow book
4 | 4.2.1.4 | Approve borrow book
4 | 4.2.1.5 | View borrowed book list
4 | 4.2.1.6 | Update ticket borrow book
4 | 4.2.1.7 | Delete ticket borrow book
3 | 4.2.2 | Return book
4 | 4.2.2.1 | Confirm return book
4 | 4.2.2.2 | View returned book list
3 | 4.2.3 | Rate and comment
4 | 4.2.3.1 | Creat rate
4 | 4.2.3.2 | Creat comment
4 | 4.2.3.3 | View comment
3 | 4.2.3 | Fix bug release 2
1 | 5 | Phase 5: Testing
2 | 5.1 | Creat Test plan
2 | 5.2 | Write testcase
2 | 5.3 | Implement test release 1
2 | 5.4 | Implement test release 2
2 | 5.5 | Implement testing in all function
2 | 5.6 | UAT
1 | 6 | Phase 6: Deployment
2 | 6.1 | Buy server
2 | 6.2 | Setting server
2 | 6.3 | Deploy code in staging enviroment
2 | 6.4 | Deploy code in product enviroment
2 | 6.5
2