## Sheet1
Sequence Project Activities
WBS ID | Task name | Predecessor
2 | Phase 2: Analyst requiremt
2.1 | Elicitation | 1.1
2.1.1 | Libararian survey | 1.1
2.1.2 | Student survey | 1.1
2.2 | Document
2.2.1 | Draw wireframe | 2.1
2.2.2 | Write SRS | 2.1
2.3 | Review + update SRS | 2.2.1, 2.2.2
3 | Phase 3: Design
3.1 | Design UI | 2.2.1
3.2 | Design DB | 2.2.2
3.3 | Design architecture system | 2.2.2
3.4 | Review DB, Architecture system | 3.2, 3.3